Department of Homeland Security (DHS)

Immigration and Customs Enforcement (ICE)

Office of the Chief Financial Officer (OCFO)

ICE Agentic Accounts Payable

Invoice Intake Automation

Discussion Document

October 2026

Provided by:

Guidehouse Inc.

Melanie Geesaman, Partner

1676 International Drive, Suite 800

McLean, VA 22102

Tel: (703) 915-9177

Email: mgeesaman@guidehousefederal.com

Taxpayer Identification Number (TIN): 36-4094854

# 1.0	Our Understanding

The ICE Office of the Chief Financial Officer (OCFO) manages the agency’s financial operations, and its Office of Financial Management (OFM) pays the vendors who support ICE’s mission. OFM’s accounts payable (AP) process begins in a shared mailbox. Vendors email their invoices, usually as PDF attachments; AP technicians read each one for the elements of a proper invoice and create a record in FileOnQ, OFM’s invoice repository and workflow tool, by entering the required fields and attaching the PDF. Records then pass through quality checks before FileOnQ routes them for receiving, acceptance, certification and payment.

On October 5, 2026, OCFO leadership and the OFM team described the mailbox review and FileOnQ record creation as the largest bottleneck in accounts payable. Every vendor presents its invoice differently, so earlier attempts at automation struggled, and technicians re-key the same information by hand. OCFO asked Guidehouse what would be built, how long it would take, what team it needs, and what it would cost, so that OCFO can plan the funding.

The objective is an agentic intake capability that automates invoice intake: it reads the invoices that arrive in the shared mailbox, extracts and checks the required data, and gives a technician a ready-to-approve record that, on approval, becomes a FileOnQ record with the PDF attached. It is agentic in that it carries out each intake step itself, from reading the email to drafting the record, while a technician approves every record. It expedites the current process rather than replacing it: FileOnQ, field approval, certification and payment are unchanged, and ICE adopts nothing new beyond a review screen for its technicians. The scope is AP invoice intake only.

# 2.0	Our Approach

Guidehouse proposes a staged approach with a decision point before any work touches live invoices. Three task areas take the effort from discovery through a working prototype to a measured evaluation with OFM technicians. Two optional task areas follow, each decided by OCFO on the results of the one before: a pilot on live invoices, then production and rollout with change management and training. Each task area ends with a gate review at which the plan, assumptions and estimate are updated. With OCFO’s agreement, each task order also requests the approvals and access the next one would need, so they are in progress before OCFO decides.

The prototype is built on synthetic invoices from fictional vendors, with no connection to any ICE system and no personal or financial data. It runs on ICE’s existing Databricks environment, confirmed with the Office of the Chief Information Officer (OCIO) in discovery, with ICE’s Azure environment as the alternative if OCIO cannot host OCFO’s work on Databricks or that environment cannot reach the mailbox. It is built in ICE’s environment, under that environment’s security controls and with full logging, so the pilot and production extend it rather than rebuild it. A single interface layer keeps the intake steps separate from the destination system, so that a later change to how invoices reach ICE’s financial system changes only that layer. The work extends Guidehouse’s Small Business Innovation Research (SBIR) Phase I effort, “Software Solution To Extract Key Information From Big Data” (Section 8.0): vendor invoices are a large, varied body of documents from which a fixed set of key fields must be extracted reliably, checked and handed to a person for decision.

## 2.1	Task Area 1: Discovery and Design

Discovery takes 3 to 5 weeks, with 4 weeks as the base, including time to onboard the Guidehouse team. Guidehouse walks through today’s intake process with OFM’s process owners and technicians, agrees on the proper-invoice checklist (drafted from FAR 32.905(b) if none is written down) and the reason codes technicians will use, times three to five technicians to set a baseline in minutes per invoice, and learns FileOnQ’s record fields and interface options. At kickoff, Guidehouse asks OCIO for the team’s workspace and accounts. With OCIO, it confirms the platform and approved services, provides a security and data-handling summary, and drafts the approvals a pilot would need, for OCFO to release at the gate review: the Information System Security Officer’s (ISSO) approval of a read-only connection to the AP mailbox, read access to FileOnQ to check pilot results against technicians’ records, any service not yet in use, and a privacy threshold analysis for ICE’s privacy office, since live invoices carry vendor banking and personal data. The task area ends with a discovery report, agreed success targets, an updated plan and a gate review with OCFO.

## 2.2	Task Area 2: Prototype Build

The build takes 5 to 7 weeks, with 6 weeks as the base, including a week of contingency for data access and connectivity. Guidehouse builds a synthetic test set of 8 to 12 invoice layouts and OFM’s edge cases, with known correct values, holding some layouts back to test whether the prototype can read a layout it has never seen. The intake service reads a test mailbox, separates invoices from other documents, extracts the agreed fields and records where each was found, comparing at least two extraction approaches, one of them model-based. It runs the agreed checklist, scores each field’s confidence and marks each invoice ready for review, needs attention, or likely improper. A field it could not read goes to the technician to check rather than into a rejection.

On the review screen the technician sees the invoice beside the extracted data, then approves, corrects or rejects with a reason code. Approval produces a FileOnQ-ready record through a mock interface; rejection drafts a vendor notice for the technician to send. Every email, extraction, edit and decision is logged. The task area ends with a demonstration to OFM’s process owners on invoices not used in development.

## 2.3	Task Area 3: Prototype Evaluation

The evaluation takes 2 to 4 weeks, with 3 weeks as the base. Three to five technicians work the review queue in timed sessions, giving minutes per invoice against the baseline. Guidehouse measures field accuracy on the held-out layouts, the rate at which invoices marked ready contain an error, the share reaching ready for review, and the detection of improper invoices; makes one improvement cycle from the technicians’ corrections; and delivers a metrics report with a pilot recommendation and estimate. At the gate review, OCFO decides whether to proceed to a pilot.

## 2.4	Task Area 4: Pilot (Optional)

The pilot is the minimum viable product: the prototype, improved from the evaluation, working on live invoices in ICE’s existing environment for a scope OCFO agrees at the Task Area 3 gate review, naming the invoice types, the pilot technicians and the targets to meet before production is considered. For this estimate, Guidehouse assumes a pilot group of three to five technicians, about four weeks in shadow mode, where the system works alongside technicians without replacing their work, and eight in assisted mode, where they work from the review queue. A FileOnQ integration is built if discovery found a viable interface. If OCFO released it at the Task Area 1 gate review, the mailbox connection is already in review. During the pilot, Guidehouse requests production’s approvals: the FileOnQ connection or bulk import, ICE’s change control, and the operating team. The pilot takes 8 to 16 weeks, with 12 as the base, and ends with results and a production recommendation.

## 2.5	Task Area 5: Production, Change Management and Rollout (Optional)

If OCFO approves the production recommendation, Guidehouse completes the system for daily use in 12 to 20 weeks, with 16 as the base: the FileOnQ connection (or bulk import if FileOnQ has no practical interface), the layouts and exceptions met in the pilot, and monitoring and recovery. Each release is tested, including for Section 508 accessibility, and accepted by OFM before it goes live through ICE’s change control. Change management starts at the same time: Guidehouse updates OFM’s desk procedures, prepares role-based training and job aids, and rolls out in groups, each trained before it goes live and supported afterwards. The task area ends with operation handed to the team ICE designates. Operation and maintenance after handover are not included and can be priced separately.

## 2.6	Out of Scope

The prototype uses no real ICE invoice data unless OCFO approves it in writing. Processing without technician review, replacing FileOnQ, and integration with the financial system or Treasury are out of scope. Extending the capability further into the payment process, or to the components ICE serves, is a possible later option once the intake results are in.

# 3.0	Project Plan

Task Areas 1 to 3 take 10 to 16 weeks from contract award to OCFO’s go or no-go decision on a pilot, and 13 weeks on the base schedule, which allows for onboarding and access to ICE’s environment. The optional pilot adds 8 to 16 weeks and production and rollout a further 12 to 20 weeks; each starts only when OCFO approves it, with its approvals already requested during the task order before. The critical path runs through OCIO’s confirmation of the platform and workspace access before the build starts.

Figure 1. Base schedule. Gate reviews fall at weeks 4 and 13, and the prototype is demonstrated at week 10. Optional task areas start only when OCFO approves them; their approvals are requested during the task order before, so they are already in progress.

| Week After Award | Milestone |
| --- | --- |
| 0 | Contract award and kickoff with OFM’s process owners and OCFO sponsors |
| Every two weeks from Week 2 | Status report to the COR and OCFO sponsors |
| 4 (range 3 to 5) | Task Area 1 gate review: discovery report, checklist, success targets, updated plan |
| 10 (range 8 to 12) | Working prototype demonstrated on invoices not used in development |
| 13 (range 10 to 16) | Task Area 3 gate review: metrics report; OCFO decides whether to proceed to a pilot |
| Pilot, if approved | Scope agreed; mailbox connection approved by the ISSO; shadow then assisted mode; production recommendation about 12 weeks later |
| Production, if approved | Approvals requested during the pilot in place; production build and change management; rollout in trained groups; handover about 16 weeks after approval |

OCFO’s time is small and scheduled: the process owners for a few hours a week during discovery and evaluation, three to five technicians for a few hours each, whoever administers FileOnQ, OCIO for the environment, and the sponsors for status reports and gate reviews.

# 4.0	Assumptions

These assumptions come from the October 5 discussion. Discovery will confirm or correct each one, and Guidehouse will propose any material change in writing before acting on it.

Environment and authorization. ICE provides, through OCIO, a workspace on its existing environment with accounts for the team in time for the build. The capability is built within that existing, authorized environment and is not a new system of record, so Guidehouse assumes no new authority to operate (ATO) is needed; the ISSO still approves the workspace, any service not already in use, and the connections to the mailbox and FileOnQ. If OCIO requires a separate authorization, Guidehouse will coordinate with OCIO and the schedule may extend. If an approval requested a stage ahead is not in place when OCFO approves the next task order, work that does not depend on it starts first.

Platform and services. Guidehouse will use only services ICE has confirmed are allowed on that environment. Any licenses are held by ICE, so no license, hosting or travel costs are in this estimate.

Process and data. Most invoices arrive as PDF attachments; scanned invoices may need character recognition and may lower accuracy. If FileOnQ has no practical interface, the pilot uses bulk import or OFM’s existing automation. Success targets are set in discovery from baseline measures, not promised in advance.

People. OFM staff, OCIO and the sponsors are available as Section 3.0 describes. Guidehouse staff hold, or can promptly obtain, the background checks and access ICE requires; if onboarding takes longer than Task Area 1 allows, the schedule moves with it.

Contract. A contract is in place before discovery begins, with time and materials (T&M) task orders under the contract in Section 8.0, so ICE pays only for work performed. The Section 9.0 rate card is proposed and subject to confirmation.

# 5.0	Level of Effort

The team is small, mostly part-time, and brought on in stages as work requires. An engagement lead in the Director labor category runs the engagement and holds the gate reviews. A manager-level developer serves as solution architect: design, the interface layer, the environment work with OCIO, and the security summary and ISSO approval requests, so no separate security position is needed. A senior business analyst and AP process specialist works with OFM on the checklist, review screen and timed sessions. Two senior developers build the prototype: the AI/ML developer joins in the last week of discovery to design extraction, and the full-stack developer starts with the build. The pilot adds a half-time test and quality lead, and production adds a full-time change management and training lead.

| Position Description | Task Area 1 (FTE) | Task Area 2 (FTE) | Task Area 3 (FTE) | Hours, Task Areas 1 to 3 | Pilot (FTE) | Production (FTE) |
| --- | --- | --- | --- | --- | --- | --- |
| Director (Engagement Lead) | 0.50 | 0.25 | 0.25 | 170 | 0.25 | 0.25 |
| Manager - Developer (Solution Architect) | 1.00 | 0.50 | 0.25 | 310 | 0.75 | 0.50 |
| Senior (Business Analyst and AP Process Specialist) | 1.00 | 0.75 | 1.00 | 460 | 0.50 | 0.50 |
| Senior - Developer (AI/ML) | 0.25 | 1.00 | 1.00 | 400 | 1.00 | 0.50 |
| Senior - Developer (Full Stack) |  | 1.00 | 0.50 | 300 | 1.00 | 1.00 |
| Senior - Developer (Test and Quality Lead) |  |  |  |  | 0.50 | 0.50 |
| Senior (Change Management and Training Lead) |  |  |  |  |  | 1.00 |
| Total hours | 440 | 840 | 360 | 1,640 | 1,920 | 2,720 |

Hours are FTE multiplied by 40 hours and the base duration: 1,640 hours for Task Areas 1 to 3, between 1,270 hours and 2,010 at the shortest and longest durations. The optional pilot is 1,920 hours and the optional production and rollout 2,720 hours.

# 6.0	Success Factors

Three things make this effort likely to succeed where earlier automation struggled. The technician stays in control: nothing reaches FileOnQ without approval, and every decision is logged. Results are measured, not projected: the prototype is scored on layouts it has never seen, and OCFO’s own technicians produce the figures on which the pilot decision rests. And ICE adopts nothing new beyond the review screen: the automation sits on top of the mailbox and FileOnQ as they are.

# 7.0	Deliverables

Each deliverable is reviewed with OFM’s process owners before the gate review that follows it. Timing is in weeks after contract award on the base schedule.

| Deliverable | Task Area | Timing |
| --- | --- | --- |
| D1 Discovery report: current process, validation checklist, FileOnQ findings, baseline | 1 | Week 4 |
| D2 Updated project plan and concept of operations | 1 | Week 4 |
| D3 Success targets and measurement method | 1 | Week 4 |
| D4 Synthetic invoice test set with known correct values | 2 | Week 6 |
| D5 Working prototype with review screen, mock FileOnQ record and audit log | 2 | Week 10 |
| D6 Security and data-handling summary for OCIO, and draft approval requests for a pilot | 1 to 2 | Week 3; drafts by Week 4 |
| D7 Metrics report against the agreed targets | 3 | Week 13 |
| D8 Pilot recommendation, with a draft pilot plan and estimate | 3 | Week 13 |
| D9 Status report to the COR and OCFO sponsors | 1 to 3 | Every two weeks from Week 2 |

# 8.0	Contracting with Guidehouse

Guidehouse recommends that ICE acquire this capability through a new sole-source Small Business Innovation Research (SBIR) Phase III award. Guidehouse holds a Phase I SBIR award on the topic “Software Solution To Extract Key Information From Big Data” (topic AFRL-RQ-WP-TR-2023-0027, contract FA8650-22-F-2335), sponsored by the Air Force Research Laboratory. Under 15 U.S.C. § 638, an agency may make a Phase III award on a sole-source basis for work that derives from, extends or completes an earlier SBIR effort, which Section 2.0 describes. A Phase III award needs no further competition, typically shortens the time to award from months to weeks, and is funded from OCFO’s own appropriations rather than SBIR funds. Guidehouse will support ICE’s contracting office with the statement of work and supporting material drawn from this document.

Guidehouse recommends that the award take the form of an indefinite-delivery, indefinite-quantity (IDIQ) contract with the rate card in Section 9.0, an ordering period and ceiling that ICE’s contracting office sets, and a first task order for Task Areas 1 to 3, so that the contract and the first work go through in one package. The pilot and production then follow as further task orders, each issued only when OCFO approves it, with no new vehicle. Guidehouse recommends time and materials (T&M) task orders.

# 9.0	Rate Card and Sample Task Orders

The estimate takes the form Section 8.0 recommends: proposed hourly rates by contract year, escalating in Years 2 and 3, and sample time and materials (T&M) task orders at Year 1 rates and base durations. Work that runs past Year 1 is billed at Year 2 rates. No other direct costs are included.

## 9.1	Rate Card

| Position Description | Description and Minimum Experience | Year 1 | Year 2 | Year 3 |
| --- | --- | --- | --- | --- |
| Director | Leads the engagement, owns delivery and holds the gate reviews with OCFO. 10 or more years of experience. | $188.20 | $193.85 | $199.67 |
| Manager - Developer | Solution architect and technical lead: design, integration, the environment and the ISSO approval requests. 6 or more years of experience. | $194.37 | $200.20 | $206.21 |
| Senior | Business analysis, accounts payable process, change management and training. 4 or more years of experience. | $117.65 | $121.18 | $124.82 |
| Senior - Developer | Software, data and AI/ML development, testing and quality. 5 or more years of experience. | $145.26 | $149.62 | $154.11 |

## 9.2	Sample Task Order 1: Discovery, Prototype Build and Evaluation

Task Order 1 is awarded with the IDIQ contract and covers Task Areas 1 to 3: 1,640 hours and $248,049.70 over 13 weeks on the base schedule (10 to 16 weeks). By task area: Task Area 1, $70,789.60; Task Area 2, $125,518.20; Task Area 3, $51,741.90.

| Position Description | Rate | Task Area 1 Hours | Task Area 2 Hours | Task Area 3 Hours | Hours | Execution |
| --- | --- | --- | --- | --- | --- | --- |
| Director (Engagement Lead) | $188.20 | 80 | 60 | 30 | 170 | $31,994.00 |
| Manager - Developer (Solution Architect) | $194.37 | 160 | 120 | 30 | 310 | $60,254.70 |
| Senior (Business Analyst and AP Process Specialist) | $117.65 | 160 | 180 | 120 | 460 | $54,119.00 |
| Senior - Developer (AI/ML) | $145.26 | 40 | 240 | 120 | 400 | $58,104.00 |
| Senior - Developer (Full Stack) | $145.26 |  | 240 | 60 | 300 | $43,578.00 |
| Total, Sample Task Order 1 |  | 440 | 840 | 360 | 1,640 | $248,049.70 |

## 9.3	Sample Task Orders 2 and 3: Pilot and Production (Optional)

Sample Task Order 2, the pilot, is 1,920 hours and $295,105.20; Sample Task Order 3, production and rollout, is 2,720 hours and $391,187.20. Both are indicative, issued only if OCFO approves them, and re-estimated at the gate review before them. With the pilot, the planning figure is about $543,000; with production and rollout as well, about $934,000.

| Position Description | Rate | Pilot Hours | Pilot Execution | Production Hours | Production Execution |
| --- | --- | --- | --- | --- | --- |
| Director (Engagement Lead) | $188.20 | 120 | $22,584.00 | 160 | $30,112.00 |
| Manager - Developer (Solution Architect) | $194.37 | 360 | $69,973.20 | 320 | $62,198.40 |
| Senior (Business Analyst and AP Process Specialist) | $117.65 | 240 | $28,236.00 | 320 | $37,648.00 |
| Senior - Developer (AI/ML) | $145.26 | 480 | $69,724.80 | 320 | $46,483.20 |
| Senior - Developer (Full Stack) | $145.26 | 480 | $69,724.80 | 640 | $92,966.40 |
| Senior - Developer (Test and Quality Lead) | $145.26 | 240 | $34,862.40 | 320 | $46,483.20 |
| Senior (Change Management and Training Lead) | $117.65 |  |  | 640 | $75,296.00 |
| Total (Indicative) |  | 1,920 | $295,105.20 | 2,720 | $391,187.20 |