## Slide 1
ICE Agentic Accounts Payable
Invoice Intake Automation
Executive Summary
Immigration and Customs Enforcement (ICE), Office of the Chief Financial Officer (OCFO)
Discussion Document | October 2026 | Provided by Guidehouse
© 2026 This document contains information which is being submitted by Guidehouse for purposes of providing U.S. Immigration and Customs Enforcement with pre-contract survey information. This document should not be considered a proposal or statement of work and may be shared with parties outside of the Government, if ICE believes it is in the Government’s best interest to do so.
Notes: Short companion to the discussion document, which carries the full detail.

## Slide 2
Guidehouse | ICE Agentic Accounts Payable Invoice Intake Automation | Discussion Document, October 2026
2
Agentic intake turns re-keying into review
OCFO’s largest accounts payable bottleneck, expedited without replacing anything
Today
Vendor emails an invoice PDF to the shared mailbox
Technician reads and checks it every vendor’s layout differs
Technician re-keys it into FileOnQ fields typed, PDF attached
Quality checks, certification, payment unchanged
With agentic intake
Reads the mailbox every email and attachment
Extracts and checks the data OFM’s proper-invoice checklist
Technician reviews and approves or corrects, or rejects
FileOnQ record created with the PDF attached
Nothing reaches FileOnQ without a technician’s approval. New for ICE: a review screen only, on ICE’s existing Databricks or Azure environment.

## Slide 3
Guidehouse | ICE Agentic Accounts Payable Invoice Intake Automation | Discussion Document, October 2026
3
A pilot decision in about 13 weeks
Weeks after contract award; 10 to 16 weeks to the pilot decision on the base schedule
Chart: 
| Discovery and Design | Prototype Build | Prototype Evaluation | Pilot (optional) | Production and Rollout (optional)
Start week | 0 | 4 | 10 | 13 | 25
Weeks | 4 | 6 | 3 | 12 | 16
Weeks 3 to 4
Discovery gate
D6 security summary and pilot approval drafts; D1 to D3 discovery report, plan, targets
Weeks 6 to 10
Prototype demonstrated
D4 synthetic test set; D5 working prototype
Week 13
Pilot decision
D7 metrics report; D8 pilot recommendation
Every two weeks
Status to the COR
D9 status report: progress, risks, decisions needed
Each gate review lets OCFO approve the next step; with OCFO’s agreement, its access and approvals are requested in the step before.

## Slide 4
Guidehouse | ICE Agentic Accounts Payable Invoice Intake Automation | Discussion Document, October 2026
4
A small team, brought on in stages
Full-time equivalents by task area; each person joins when there is work for them
Discovery
Build
Evaluation
Pilot*
Production*
Director (Engagement Lead)
0.50
0.25
0.25
0.25
0.25
Manager - Developer (Solution Architect)
1.00
0.50
0.25
0.75
0.50
Senior (Business Analyst and AP Process Specialist)
1.00
0.75
1.00
0.50
0.50
Senior - Developer (AI/ML)
0.25
1.00
1.00
1.00
0.50
Senior - Developer (Full Stack)
1.00
0.50
1.00
1.00
Senior - Developer (Test and Quality Lead)
0.50
0.50
Senior (Change Management and Training Lead)
1.00
Hours
440
840
360
1,920
2,720
*Optional. The solution architect also prepares the security summary and ISSO approval requests.
Key assumptions
Environment. ICE’s existing, authorized platform and not a new system of record, so no new ATO is expected; the ISSO still approves the workspace and connections.
Data. Synthetic invoices only until an approved pilot; the pilot’s access is drafted in discovery.
People. A few scheduled hours from OFM staff, OCIO and the sponsors.
Cost. Time and materials task orders; ICE holds any licenses; no other direct costs or travel.

## Slide 5
Guidehouse | ICE Agentic Accounts Payable Invoice Intake Automation | Discussion Document, October 2026
5
One IDIQ contract, three task orders
Proposed hourly rates by contract year; sample task orders priced time and materials at Year 1 rates
Position | Year 1 | Year 2 | Year 3
Director | $188.20 | $193.85 | $199.67
Manager - Developer | $194.37 | $200.20 | $206.21
Senior | $117.65 | $121.18 | $124.82
Senior - Developer | $145.26 | $149.62 | $154.11
Task Order 1 is awarded with the IDIQ, so the contract and the first work go through in one package.
Task Orders 2 and 3 follow only if OCFO approves them, each re-estimated at the gate review before it.
Sustainment after handover can be priced as a further task order.
Task Order 1
Discovery, prototype and evaluation
$248,049.70
13 weeks | 1,640 hours
Task Order 2 (optional)
Pilot on live invoices
$295,105.20
12 weeks | 1,920 hours
Task Order 3 (optional)
Production, change management and rollout
$391,187.20
16 weeks | 2,720 hours
Planning figures: about $543,000 with the pilot; about $934,000 with production and rollout. No other direct costs.